## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | 2019-06-29 | 2019-07-10 | 2019-08-18
Iterasi 1
| Design Function | 2019-06-10 | 2019-06-11 | 0 | 2 | Ariel | 100%
| Login + Home Screen BLoC (Business Logic) | 2019-06-11 | 2019-06-15 | 2 | 5 | Ariel | 100%
| Offline Mode | 2019-06-17 | 2019-06-18 | 8 | 2 | Ariel | 100%
| Owner - Daftar Vessel | 2019-06-18 | 2019-06-19 | 10 | 2 | Ariel | 40%
| All - Create Profile | 2019-06-20 | 2019-06-21 | 13 | 2
| Owner - Vessel Management | 2019-06-21 | 2019-06-22 | 15 | 2
Iterasi 2
| Owner - Tambah User | 2019-06-22 | 2019-06-23 | 17 | 2 | Ariel | 100%
| Owner - User Management | 2019-06-23 | 2019-06-24 | 19 | 2 | Ariel | 80%
| Vessel Master - Buat Fnding | 2019-06-24 | 2019-06-29 | 21 | 6 | Wiradani | 60%
Iterasi 3
| Surveyor/Super Intendent - Finding Confirmation | 2019-06-30 | 2019-07-03 | 28 | 4 | Nathan | 100%
| Surveyor - List Job Vessel | 2019-07-03 | 2019-07-04 | 32 | 2 | Meredith | 80%
| UI/UX | 2019-07-04 | 2019-07-10 | 34 | 7 | Brandon | 60%
Iterasi 4
| API Contact | 2019-07-11 | 2019-07-15 | 41 | 5 | Nathan | 100%
| Sync Offline/Online | 2019-07-15 | 2019-07-20 | 46 | 6 | Meredith | 80%
| Image Control | 2019-07-20 | 2019-07-25 | 52 | 6 | Michael | 60%
| Revisi | 2019-07-25 | 2019-08-18 | 58 | 25 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1